EXAMPLE OF TASK MANAGEMENT MATRIX

FOR SUMMER READING PROGRAM

| Task | When to occur | Responsible Person | Update on task |
| --- | --- | --- | --- |
| Ascertain WSL summer reading theme | Fall 06 | YA/Children’s Librarian @ public library | Done |
| Meet to coordinate theme use & plan implementation | November 06 | PL and School librarians | PL inviting School personnel to meeting on this |
| Announce next summer’s theme for reading | December 06 | PL and School library: director of each |  |
| Prepare packages for all libraries participating in summer reading program | February 07 | PL staff – supervised by YA/Children’s librarian – need to contain X elements | These will need to go to all types of libraries, summer camps, daycares, youth clubs |
| Distribute all packages, do marketing for summer reading | Spring 07 | PL and school librarians contact all sites and all media contact points | A list of possible media sites will be generated by staff for this action. |
| Sign-up summer reading participants | May 07 | All staff at both public and school sites | Contacts remade at all sites, schools and clubs especially focused upon. |
| Kick off Summer Reading program | June 07 | Public librarians |  |
| Report summer reading actions | September 07 | Public library staff | These reports go again to schools for their recognition of students in program |
| Report of summer reading activities to media | September 07 | Public library staff | A media announcement can be done and sent to multiple locations for their use. |